## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team and Freshman Seminar acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions, cross-team testing, and Freshman Seminar testing.
Team Name | Your team name as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers
Testing Team Name | fill in when doing cross-team or Freshman Seminar testing

## Test Plan
User Story | Acceptance Criterion | Sprint 1 | Tester initials; date; comments (required if test failed) | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a Player I want to sign-in so that I can play a game of checkers. | Given that I have not yet signed in when I see the Home page then I must see a means to sign-in. (such as a link or button) | Pass | Alexis Chiang; 3/3/21
| Given that I am not signed-in when I do click on the sign-in link then I expect to be taken to the Sign-in page, with a means to enter a player name. | Pass | Alexis Chiang; 3/3/21
| Given that no one else is using my name when I enter my name containing at least one alphanumeric character and optionally spaces in the sign-in form and click the Sign-in button then I expect the system to reserve my name and navigate back to the Home page. | Pass | Alexis Chiang; 3/3/21
| Given that I am on the Sign-in page when I enter a name that does not contain at least one alphanumeric character or contains one or more characters that are not alphanumeric or spaces and click the Sign-in button then I expect the system to reject this name and return the Sign-in page. | Pass | Tyler Talarico; 3/10/21
| Given that someone else with my name has signed-in when I enter my name in the Sign-in form and click the Sign-in button then I expect the system to reject my sign-in and return the Sign-in page for me to try a different name. | Pass | Alexis Chiang; 3/3/21
| Given that I am signed-in when I navigate to the Home page then I expect to see a list of all other signed-in players. (NOTE: in the next story you will use this list to pick opponents for checkers games.) | Pass | Alexis Chiang; 3/3/21
| Given that I am not signed-in when I navigate to the Home page then I expect to see a message of how many players are signed-in but not a list of them (for privacy reasons). | Pass | Tyler Talarico; 3/10/21
As a Player I want to start a game so that I can play checkers with an opponent. | Given that I'm signed in when I view the Home page then I can start a game by selecting a player listed on the Home page. | Pass | Jack Sipley, 3/10/2021
| Given that the player I selected isn't yet in a game when I select that player then the system will begin a checkers game and assign me as the starting (Red) player and my opponent as the White player. | Pass | Jack Sipley, 3/10/2021
| Given that the player I selected is already in a game when I select that player then the system will return me to the Home page with an error message. | Pass | Jack Sipley, 3/10/2021, Player will not get a message saying that the other player is playing a game, but nothing happens as they stay on the home page
| Given that I'm waiting for a game when another player selects a game with me then the system will automatically send me to the Game View as the White player. NOTE: the `home.ftl` HTML includes a `<meta>` tag that tells the browser to refresh the game every 5 seconds; thus you need to update the `GetHomeRoute` controller to handle the situation when a player is assigned a game. | Pass | Jack Sipley, 3/10/2021
| Given a valid, initial game board when I drag a piece to a white space then the piece should not be droppable. | Pass | Jack Sipley, 3/10/2021
| Given a valid, initial game board when I drag a piece to an occupied space then the piece should not be droppable. | Pass | Jack Sipley, 3/10/2021
| Given a valid, initial game board when I drag a piece to an open space then the piece should be droppable. NOTE: In this Story the drop action should not do anything; piece movement will be the focus of future stories. | Pass | Jack Sipley, 3/10/2021
| Given a valid, initial game board when I view the board in the browser then my pieces are oriented on the bottom of the board grid just like I would see the board if I were playing in the physical world. | Pass | Jack Sipley 3/10/2021
As a Player I want to move my pieces to vacant locations so that I can play checkers. | Given my piece is next to a vacant spot when I move my piece then I should only have the option to move to a vacant spot. |  |  | Pass | Aaron Schulte 3/29/21
| Given my piece is a checker when I move my piece then I should only be able to move to a spot diagonally. |  |  | Pass | Aaron Schulte 3/29/21
| Given my piece is located on a white square when I move my piece then I should not be able to drop it. |  |  | Pass | Aaron Schulte 3/29/21
| Given there is already a piece on a space when I drop my piece of that space then I should not be able to drop it. |  |  | Pass | Aaron Schulte 3/29/21
As a Player I want to jump my opponent’s pieces to capture them so that I can win. | Given my piece can Simple Move to a square where there's an enemy piece, and there's a vacant square diagonal the both my piece and opponent piece when I move my piece towards the enemy piece then my piece will jump over the enemy piece and land in the vacant spot. |  |  | Pass | Aaron Schulte 3/29/21
| Given my piece is next to an enemy piece when I jump over the enemy piece then I should capture the enemy piece, where it's taken off the board. |  |  | Pass | Aaron Schulte 3/29/21
| Given that the checker has a piece in which it can jump, a jump move has to be made the piece which can be captured |  |  |  |  | Pass | Aaron Schulte 4/14/21
As a Player I want to continue jumping my opponent’s pieces if possible so that I can win. | Given there is another jumpable piece when I jump an opponent's piece then I must jump over that piece. |  |  | Fail | Aaron Schulte 3/29/21 | Pass | Aaron Schulte 4/14/21
| Given there are multiple jumpable pieces when I jump an opponent's piece then I must choose which piece to jump over. |  |  | Fail | Aaron Schulte 3/29/21 | Pass | Aaron Schulte 4/14/21
As a Player I want to sign-out so that I can stop playing. | Given that I'm signed in when I'm on the homepage then I should see an option where I can sign out (such as a button or link) |  |  | Pass | Aaron Schulte 3/29/21 | Pass | Aaron Schulte 4/14/21
| Given that I'm signed in when I hit a button or link to log out then I will be signed out and redirected back to the homepage. |  |  | Pass | Aaron Schulte 3/29/21 | Pass | Aaron Schulte 4/14/21
| Given that I signed out mid-game, it will count as a resignation and the opponent will win the game. |  |  |  |  | Pass | Aaron Schulte 4/14/21
As a Player I want the game to end when I have won or lost so that I decide what to do after. | Given I capture my opponent's last piece when I jump their last piece then I expect to be shown a victory screen and have the option to exit the game. |  |  | Fail | Aaron Schulte 3/29/21 | Pass | Aaron Schulte 4/14/21
| Given I have zero remaining pieces when my opponent captures my last piece then I expect to be shown a loss screen and have the option to exit the game. |  |  | Fail | Aaron Schulte 3/29/21 | Pass | Aaron Schulte 4/14/21
| Given that my opponent successfully resigns when my opponent clicks the resign button then I expect to be shown a victory screen and have the option to exit the game. |  |  | Fail | Aaron Schulte 3/29/21 | Pass | Aaron Schulte 4/14/21
| Given that I successfully resign when I click the resign button then I expect to be sent back to the home screen. |  |  | Fail | Aaron Schulte 3/29/21 | Pass | Aaron Schulte 4/14/21
As a Player I want my pieces to be kinged when they reach the end of the board so that my checker can move/jump forward or backwards. | Given that my piece isn't a king when it reaches the board, then piece should be made king when it reaches the end of the board. |  |  |  |  | Pass | Aaron Schulte 4/14/21
| Given that my piece is a king, then I should have the option to move forward or backwards. |  |  |  |  | Pass | Aaron Schulte 4/14/21
| Given that my piece isn't a king, when my piece reaches the end of the board, then the piece should be made a king and end my turn. |  |  |  |  | Pass | Aaron Schulte 4/14/21
As a Player I want to be able to resign at any point during a game so that I can quit or start another. | Given that I'm in a game, when I resign, then the game should end and declare my opponent as the winner. |  |  |  |  | Pass | Aaron Schulte 4/14/21
| Given that I'm in a game, when my opponent resigns, then the game should end and declare me as the winner. |  |  |  |  | Pass | Aaron Schulte 4/14/21
As a player, I should be able to view a live game that I'm not playing | Given that I'm signed in and not playing a game, then I should be able to join a game where I'm just spectating. | [5 empty] | Not Implemented
| Given that I'm spectating a game between two players, then then there should be an exit button that redirects me to the homepage. | [5 empty] | Not Implemented
| Given that I'm spectating a game between two players, when I sign out, then I should be removed from the spectator list and experience the all benefits of being signed out. | [5 empty] | Not Implemented
As a player I want to send or receive a message whenever a rematch is offered. | Given there is a dialogue box when I am playing an opponent then I expect to be able to read messages sent by them. |  |  |  |  | Pass | Aaron Schulte 4/14/21
| Given there is a dialogue box when I am playing an opponent then I expect to be able to type a message and send it to them. |  |  |  |  | Pass | Aaron Schulte 4/14/21
| Given that I'm in a game, when the game is over, then I should have the option to offer a rematch to my opponent. |  |  |  |  | Pass | Aaron Schulte 4/14/21
As the player I want another game displayed when asked to play another game. | Given that I am in the middle of a game, when I click "Home" then I expect my game to be saved and to be sent to the homepage |  |  |  |  | Pass | Aaron Schulte 4/14/21
| Given that I am on the homepage when I have unfinished games then I expect to be see them on the homepage |  |  |  |  | Pass | Aaron Schulte 4/14/21
| Given that I have an unfinished game when I click the game then I expect my game to continue where I left off |  |  |  |  | Pass | Aaron Schulte 4/14/21
| Given I am playing a game when a player sends me a new game request then I expect to be given a choice to accept or decline |  |  |  |  | Pass | Aaron Schulte 4/14/21